## DP Gantt Chart
HDL Project
Department of Engineering, CvSU-CCAT
Project Leader: Kurt Neil Ashly Agliday |  | Project Start: |  | 2022-12-01
Members:
Anthoneth Hernandez
Jenrie Mae B. Casibu
Jose Jerry Crema
Michaella M. Madlangbayan
Nemson Sarinas
Adviser: Engr. Marc Joshua Prudente |  | Display Week: |  | 1 |  |  | 2022-12-01 | [6 empty] | 2022-12-08 | [6 empty] | 2022-12-15 | [6 empty] | 2022-12-22 | [6 empty] | 2022-12-29 | [6 empty] | 2023-01-05 | [6 empty] | 2023-01-12
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. | time axis 2022-12-01 to 2023-01-18
WBS | TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2022-12-01 to 2023-01-18
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
1 | Phase 1 Design Project Outline | All Members | 100% | 2021-12-01 | 2022-12-01 | bar: 2022-12-01 to 2023-01-18
1.1 | Title conceptualization (at least 1) | ALL MEMBERS | 100% | 2022-12-01 | 2022-12-06 | 6 | bar: 2022-12-01 to 2023-01-18
1.1.1 | > Submit titles to adviser | ALL MEMBERS | 100% | 2022-12-01 | 2022-12-03 | 3 | bar: 2022-12-01 to 2023-01-18
1.1.2 | > Approve and reject title(s) | ALL MEMBERS | 100% | 2022-12-03 | 2022-12-04 | 2 | bar: 2022-12-01 to 2023-01-18
1.1.3 | > Review approved title(s) | ALL MEMBERS | 100% | 2022-12-04 | 2022-12-06 | 3 | bar: 2022-12-01 to 2023-01-18
1.1.4 | > Recommend technical critic | ALL MEMBERS | 100% | 2020-10-01 | 2020-10-03 | 3 | bar: 2022-12-01 to 2023-01-18
1.2 | Preparation of Outline Proposal | ALL MEMBERS | 100% | 2022-12-06 | 2022-12-27 | 22 | bar: 2022-12-01 to 2023-01-18
1.2.1 | > Write [Chapter 1 - Introduction] | ALL MEMBERS | 100% | 2022-12-06 | 2022-12-11 | 6 | bar: 2022-12-01 to 2023-01-18
1.2.1.1 | >> Write [Objectives of the study] | ALL MEMBERS | 100% | 2022-12-06 | 2022-12-07 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.1.1 | >> Write [Significance of the study] | ALL MEMBERS | 100% | 2022-12-07 | 2022-12-08 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.1.1 | >> Write [Time and place of the study] | ALL MEMBERS | 100% | 2022-12-08 | 2022-12-09 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.1.1 | >> Write [Scope and limitations] | ALL MEMBERS | 100% | 2022-12-09 | 2022-12-10 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.1.1 | >> Write [Conceptual framework] | ALL MEMBERS | 100% | 2022-12-10 | 2022-12-11 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.2 | > Write [Chapter 2 - Review of Related Literature] | ALL MEMBERS | 100% | 2022-12-06 | 2022-12-27 | 22 | bar: 2022-12-01 to 2023-01-18
1.2.2.1 | >> Write [Related Literature] | ALL MEMBERS | 100% | 2022-12-06 | 2022-12-27 | 22 | bar: 2022-12-01 to 2023-01-18
1.2.2.2 | >> Write [Synthesis and Justification] | ALL MEMBERS | 100% | 2022-12-25 | 2022-12-27 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.3 | > Write [Chapter 3 - Review of Related Literature] | ALL MEMBERS | 100% | 2022-12-11 | 2022-12-27 | 17 | bar: 2022-12-01 to 2023-01-18
1.2.3.1 | >> Write [Description of the project/technology] | ALL MEMBERS | 100% | 2022-12-11 | 2022-12-13 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.3.2 | >> Write [Design, fabrication, and procurement procedures] | ALL MEMBERS | 100% | 2022-12-14 | 2022-12-18 | 5 | bar: 2022-12-01 to 2023-01-18
1.2.3.3 | >> Write [Principles of operation] | ALL MEMBERS | 100% | 2022-12-19 | 2022-12-21 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.3.4 | >> Write [Testing and Evaluation] | ALL MEMBERS | 100% | 2022-12-22 | 2022-12-24 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.3.5 | >> Write [Data Analysis] | ALL MEMBERS | 100% | 2022-12-25 | 2022-12-27 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.4 | Outline Proposal Review | ALL MEMBERS | 100% | 2020-11-16 | 2020-11-27 | 12 | bar: 2022-12-01 to 2023-01-18
1.2.4.1 | > Submit [Outline Proposal] to adviser & critic | ALL MEMBERS | 100% | 2020-11-16 | 2020-11-17 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.4.2 | > Review [Outline Proposal] | ALL MEMBERS | 100% | 2020-11-18 | 2020-11-19 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.4.3 | > Modify [Outline Proposal] as recommended | ALL MEMBERS | 100% | 2020-11-20 | 2020-11-21 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.4.4 | > Submit [Outline Proposal] to research coordinator | ALL MEMBERS | 100% | 2020-11-22 | 2020-11-23 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.4.5 | > Review [Outline Proposal] | ALL MEMBERS | 100% | 2020-11-24 | 2020-11-25 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.4.6 | > Modify [Outline Proposal] as recommended | ALL MEMBERS | 100% | 2020-11-26 | 2020-11-27 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.5 | Outline Defense | ALL MEMBERS | 100% | 2020-11-30 | 2020-12-11 | 12 | bar: 2022-12-01 to 2023-01-18
1.2.5.1 | > Request for [Defense Schedule Slot] | ALL MEMBERS | 100% | 2020-11-30 | 2020-12-04 | 5 | bar: 2022-12-01 to 2023-01-18
1.2.5.2 | > Submit [Request for Outline Defense] w/ adviser & critic signature | ALL MEMBERS | 100% | 2020-11-30 | 2020-12-04 | 5 | bar: 2022-12-01 to 2023-01-18
1.2.5.3 | > Forward the [Request letters] to signatories | ALL MEMBERS | 100% | 2020-12-07 | 2020-12-08 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.5.4 | > Finalize [Defense Schedule Slot] | ALL MEMBERS | 100% | 2020-12-08 | 2020-12-11 | 4 | bar: 2022-12-01 to 2023-01-18
1.2.5.5 | > Submit [Finalized Defense Schedule] to ODI | ALL MEMBERS | 100% | 2020-12-11 | 2020-12-11 | 1 | bar: 2022-12-01 to 2023-01-18
1.2.5.6 | > Day of the Defense | ALL MEMBERS | 100% | 2021-01-06 | 2021-01-08 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.5.7 | >> Present and defend the [Outline Proposal] | ALL MEMBERS | 100% | 2021-01-06 | 2021-01-08 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.5.8 | >> Facilitate the [On-going Defense] | ALL MEMBERS | 100% | 2021-01-06 | 2021-01-08 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.5.9 | >> Review the proposal by tackling and recommending important points regarding the study. | ALL MEMBERS | 100% | 2021-01-06 | 2021-01-08 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.5.10 | >> Help students defending [Maximum of 5 chances] | ALL MEMBERS | 100% | 2021-01-06 | 2021-01-08 | 3 | bar: 2022-12-01 to 2023-01-18
1.2.6 | Outline Approval | ALL MEMBERS | 100% | 2021-01-07 | 2021-01-15 | 9 | bar: 2022-12-01 to 2023-01-18
1.2.6.1 | > Accomplish [Recommendation and Compliance Form] | ALL MEMBERS | 100% | 2021-01-08 | 2021-01-09 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.6.2 | > Check the [Recommendation and Compliance Form] | ALL MEMBERS | 100% | 2021-01-09 | 2021-01-10 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.6.3 | > Review the [Recommendation and Compliance Form] | ALL MEMBERS | 100% | 2021-01-09 | 2021-01-10 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.6.4 | > Modify [Recommendation and Compliance Form] as needed | ALL MEMBERS | 100% | 2021-01-10 | 2021-01-10 | 1 | bar: 2022-12-01 to 2023-01-18
1.2.6.5 | > Modify [Outline Proposal] as needed | ALL MEMBERS | 100% | 2021-01-10 | 2021-01-15 | 6 | bar: 2022-12-01 to 2023-01-18
1.2.6.5.1 | >> Finalize system design (schematic, flow charts, wiring diagrams, system block diagram, algorithm, programming language) | ALL MEMBERS | 100% | 2021-01-10 | 2021-01-11 | 2 | bar: 2022-12-01 to 2023-01-18
1.2.6.5.2 | >> Finalize fabrication method - [THIS IS VERY IMPORTANT] | ALL MEMBERS | 100% | 2021-01-11 | 2021-01-12 | bar: 2022-12-01 to 2023-01-18
1.2.6.5.3 | >> Finalize materials procurement plan (what/when/where to buy and quantity) | ALL MEMBERS | 100% | 2021-01-12 | 2021-01-13 | bar: 2022-12-01 to 2023-01-18
1.2.6.5.4 | >> Finalize all testing and evaluation tables | ALL MEMBERS | 100% | 2021-01-13 | 2021-01-13 | bar: 2022-12-01 to 2023-01-18
1.2.6.5.5 | >> Finalize Gantt Chart | ALL MEMBERS | 100% | 2021-01-13 | 2021-01-13 | bar: 2022-12-01 to 2023-01-18
1.2.6.6 | > Submit [Outline Approval Form] to research coordinator w/ signatures of adviser and critic | ALL MEMBERS | 100% | 2021-01-13 | 2021-01-14 | bar: 2022-12-01 to 2023-01-18
1.2.6.7 | > Forward [Outline Approval Form] to signatories | ALL MEMBERS | 100% | 2021-01-14 | 2021-01-14 | bar: 2022-12-01 to 2023-01-18
1.2.6.8 | > Submit [List of Approved Outline Proposals] to ODI | ALL MEMBERS | 100% | 2021-01-15 | 2021-01-15 | bar: 2022-12-01 to 2023-01-18
2 | Phase 2 Fabrication | All Members | 100% | 2022-12-02 | 2022-12-21 | 20 | bar: 2022-12-01 to 2023-01-18
2.1 | Programming | All Members | 100% | 2022-12-02 | 2022-12-08 | 7 | bar: 2022-12-01 to 2023-01-18
| Testing of the program | All Members | 100% | 2022-12-09 | 2022-12-15 | 7 | bar: 2022-12-01 to 2023-01-18
| Debugging | All Members | 100% | 2022-12-16 | 2022-12-21 | 6 | bar: 2022-12-01 to 2023-01-18
3 | Phase 3 Testing and Evaluation | All Members | 100% | 2022-12-22 | 2023-01-06 | 16 | bar: 2022-12-01 to 2023-01-18
| Task 1: Unit testing | All Members | 100% | 2022-12-22 | 2022-12-25 | 4 | bar: 2022-12-01 to 2023-01-18
| Task 2: Integration testing | All Members | 100% | 2022-12-26 | 2022-12-29 | 4 | bar: 2022-12-01 to 2023-01-18
| Task 3: System testing | All Members | 100% | 2022-12-30 | 2023-01-02 | 4 | bar: 2022-12-01 to 2023-01-18
| Task 5: Optimization | All Members | 100% | 2023-01-03 | 2023-01-06 | 4 | bar: 2022-12-01 to 2023-01-18
4 | Phase 4 Final Documentation |  |  | 2023-01-07 | 2023-01-15 | 9 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -1 | -1 | -1
| Task 1: Writing Chapter 4 (Results and Discussion) |  | 0% | bar: 2022-12-01 to 2023-01-18
| Task 2: Writing Chapter 5 (Summary, Conclusion and Recommendations) |  | 0% | bar: 2022-12-01 to 2023-01-18
| Task 3: Draft manuscript (preliminary pages, chapters 1-5, appendices) |  | 0% | bar: 2022-12-01 to 2023-01-18
| Task 4: Submit to adviser and technical critic for critiquing |  | 0% | bar: 2022-12-01 to 2023-01-18
| Task 5: Revise papers |  | 0% | bar: 2022-12-01 to 2023-01-18
| SPARE DAYS FOR OTHER SUBJECT EXAMINATIONS, UNIVERSITY EVENTS and OTHER MATTERS |  | 0% | 1899-12-31 | 1900-01-05 | 6 | bar: 2022-12-01 to 2023-01-18
| Documentation |  | 100% | 2023-01-07 | 2023-01-15 | 9 | bar: 2022-12-01 to 2023-01-18
[7 empty] | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1 | -1
i | bar: 2022-12-01 to 2023-01-18
This row marks the end of the Project Schedule. DO NOT enter anything in this row. Insert new rows ABOVE this one to continue building out your Project Schedule. | Insert new rows ABOVE this one
Note on A1: Self Service Issued Certificate Printing Kiosk For The Barangay
Note on A12: Work Breakdown Structure
Note on A68: The next rows below are examples only. However, this is used by the previous batch.